## Development Log
Mixed Reality Construction Software Engineering Project Log
Summary
Project | Construction AR Platform | [8 empty] | Hourly Rate | 125
Prepared | 2026-08-06 | [8 empty] | Billable Hours
Purpose | Track engineering time, billing, deliverables, and major technical decisions. | [8 empty] | Amount Due
Date | Start Time | End Time | Hours | Category | Task / Summary | Deliverable | Git Commit / Version | Billable | Notes
2026-08-03 | 9:00 | 10:15 |  | Planning | Reviewed client vision and drafted the initial project scope to preserve the requested product direction while defining MVP boundaries. | construction-ar-project-scope.md | Week 1 local draft | Yes | Established the week 1 scope baseline and phased roadmap.
2026-08-04 | 9:00 | 10:15 |  | Requirements | Expanded the scope into a formal requirements document and system architecture outline tied to the scan-place-save-share MVP workflow. | construction-ar-requirements-document.md; construction-ar-system-architecture.md | Week 1 local draft | Yes | Converted the client vision into buildable product and technical requirements.
2026-08-05 | 9:00 | 10:30 |  | Planning | Built the MVP feature breakdown and backlog structure to sequence implementation work and keep future-phase items out of the first release. | construction-ar-mvp-feature-breakdown.md; construction-ar-mvp-backlog-breakdown.md | Week 1 local draft | Yes | Created the implementation-ready planning stack for the first release.
2026-08-06 | 9:00 | 10:00 |  | Setup | Scaffolded the launchable application shell in the working folder using a minimal Expo React Native TypeScript structure with placeholder MVP modules only. | construction-ar-platform scaffold | Local scaffold created | Yes | No features were implemented; this established the starter codebase only.
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
2026-08-11 | 9:00 | 9:40 |  | Planning | Reviewed MVP documents and translated scope into a phased build plan. | mvp-build-plan.md |  | Yes | Defined milestone order for project setup, scanning, placement, validation, outputs, and hardening.
2026-08-11 | 9:40 | 10:20 |  | Requirements | Compared the active repo against the MVP plan and documented implementation gaps. | repo-vs-mvp-gap-analysis.md |  | Yes | Identified missing scanning, placement, persistence, validation, and output capabilities.
2026-08-11 | 10:20 | 11:05 |  | Setup | Added core domain models and the project document schema for the mobile app. | src/domain/*; src/storage/projectDocument.ts |  | Yes | Defined Project, RoomCapture, Surface, CatalogObject, PlacedObject, anchor, and validation structures.
2026-08-11 | 11:05 | 11:40 |  | Setup | Expanded the app shell into a project workspace with persistence, starter catalog, and validation scaffolding. | src/features/home/HomeScreen.tsx; src/storage/projectRepository.ts; src/domain/validationService.ts |  | Yes | Enabled project creation, room entries, object listing, and saved project state.
2026-08-11 | 11:40 | 12:10 |  | Setup | Integrated the live camera preview flow and prepared the iOS development build path. | src/features/camera/LiveCameraScreen.tsx; app.json; package.json |  | Yes | Added rear-camera preview, camera permissions, and native build support for physical device testing.
2026-08-11 | 12:10 | 12:45 |  | Setup | Verified the phone-to-laptop streaming milestone on a physical iPhone and browser receiver. | WebRTC phone-to-laptop demo verified |  | Yes | Worked through Xcode signing, Developer Mode, path cleanup, device install, and browser/signaling setup to confirm a working live connection.

## Milestones
Milestone | Description | Status | Start Date | Completion Date | Estimated Hours | Actual Hours | Variance | Notes
Project Setup | Initial planning, scope, and environment preparation | Completed | 2026-08-03 | 2026-08-06 | 5 | 5 |  | Week 1 focused on planning, technical documentation, and starter app scaffolding.
Spatial Scanning Prototype | Evaluate mixed reality scene understanding and mapping | Not Started | [5 empty] | Deferred until MVP build work begins.
Object Placement Workflow | Prototype anchored model placement in jobsite context | Not Started | [5 empty] | Deferred until MVP build work begins.
Collaboration & Sync | Define multi-user or shared-state requirements | Not Started | [5 empty] | Deferred until MVP build work begins.
MVP Readiness | Stabilization, QA, and client demo package | Not Started | [5 empty] | Deferred until MVP build work begins.

## Architecture Decisions
Date | Topic | Decision | Reasoning | Alternatives Considered
2026-08-03 | Scope Control | Treat week 1 as documentation and scaffold setup rather than feature implementation. | The client vision is broad, so MVP boundaries had to be defined before development could proceed responsibly. | Jumping directly into scanning, placement, or multi-platform features without an agreed MVP baseline.
2026-08-04 | MVP Definition | Anchor the first release around a scan-place-save-share workflow. | This is the smallest end-to-end loop that demonstrates value while preserving the longer platform vision. | Including clash detection, collaboration, blueprint generation, or enterprise reporting in the first release.
2026-08-06 | App Scaffold | Start with a minimal Expo React Native TypeScript shell for the code scaffold. | It provides a fast, launchable mobile app structure without prematurely committing feature logic. | Starting with a fully native or multi-runtime implementation before the app shell and module boundaries existed.

## Lessons Learned
Date | Problem | Cause | Solution | Time Lost | Preventative Action
2026-08-03 | The original concept spans multiple products, not a single MVP. | The client vision combines visualization, coordination, documentation, and future automation in one platform statement. | Created separate scope, requirements, architecture, and MVP planning documents before writing feature code. | 0.25 | Require phased roadmap language at project start whenever the vision mixes near-term and long-term capabilities.
2026-08-06 | Primary device selection is a gating decision for build work. | The target hardware list includes phones plus headset platforms with different runtime constraints. | Captured device selection as an explicit decision gate and limited week 1 coding to a launchable app shell only. | 0.25 | Confirm the first MVP device family before implementing scanning, placement, or persistence features.

## Feature Registry
Feature | Status | Primary Files | Date Started | Date Completed | Owner
Spatial Scan Intake | In Planning | construction-ar-project-scope.md; construction-ar-requirements-document.md; construction-ar-mvp-feature-breakdown.md | 2026-08-03 |  | Steve Marlow
Anchored Object Placement | Not Started | TBD during MVP build phase |  |  | Steve Marlow
Jobsite Measurement Overlay | Not Started | TBD during MVP build phase |  |  | Steve Marlow
Session Persistence | Not Started | TBD during MVP build phase |  |  | Steve Marlow
Client Demo Build | In Progress | construction-ar-platform/App.tsx; construction-ar-platform/src/app/AppShell.tsx; construction-ar-platform/src/features/home/HomeScreen.tsx | 2026-08-06 |  | Steve Marlow